## 3.5-Day Review Plan
Albertsons 3.5-Day Enterprise AI Architecture Intensive
Program design: The original learning journey is retained in a 3.5-day architect-level format. Environment setup, model deployments, ML endpoints, RAG index, specialist agents, MCP server, tracing and starter code are completed before the program. Live sessions focus on architecture judgment, guided integration, evaluation, governance and one connected retail decision workflow.
Mandatory Pre-Program Readiness (To be Completed and Tested one week before Training)
Area | Participant Readiness | Preconfigured Azure Assets | Trainer-Provided Lab Assets | Validation Check | Purpose | Ownership
Access & tools | VS Code, Python, vendor provided sharepoint repository access, approved packages and Azure sign-in tested Albertsons Enterprise Claude access to be extended to all paticipants and are able to access via VSCode code assistant succesfully. | Foundry project, GPT and embedding deployments, AI Search, monitoring and shared runtime | Starter repository, configuration files and completed backup versions | Participant smoke test: login → model call → Search query → trace visibility | Eliminate classroom setup and troubleshooting time | Client Azure admin + trainer
Prebuilt services | No participant model training or infrastructure creation required | Forecast, recommendation and SLM endpoints; action API; dummy MCP server | Prepared RAG index, synthetic datasets, specialist agents and evaluation set | End-to-end trainer dry run completed before delivery | Preserve learning breadth while reducing build depth | Trainer
Connected Retail Business Storyline Across All 3.5 Days
Stage | Retail Decision | Primary Technology | Business Value | Illustrative KPIs | Architecture Evidence | Delivered In
1 | Identify sales, inventory and promotion exceptions | Analytics / BI | Prioritize products, stores and customer segments requiring attention | Analysis time; numeric accuracy; exception coverage | Trusted source metrics and business-value baseline | Day 1
2 | Estimate demand and rank relevant offers | Classical ML | Reduce stockout exposure and improve offer relevance | Forecast error; Precision@K; conversion; margin | Model contract, confidence and explainability output | Day 1
3 | Compare promotion and inventory scenarios | ML + deterministic simulation | Improve promotion and allocation decisions | Projected sales; margin; scenario variance | Assumptions, uncertainty and human-review decision | Day 1
4 | Structure the request and validate policy | GenAI + RAG | Convert business requests into grounded recommendations | Extraction accuracy; citation accuracy; groundedness | Validated JSON, retrieved evidence and escalation rules | Day 2
5 | Coordinate specialists and select next best action | Multi-agent orchestration | Combine predictive, policy and operational capabilities | Routing accuracy; latency; decision completeness | Agent contracts, shared state and stopping conditions | Day 3
6 | Execute an approved enterprise action | MCP/API + human approval | Reduce manual hand-offs without losing control | Approval compliance; action success; trace completeness | MCP boundary, audit trail and production-readiness evidence | Day 3
Daily Session Duration: 6.5 Hours Excluding Breaks
DAY 1 ¦ Business Value, Technology Triage, ML Explainability and What-If Analysis
Day objective: Establish the business case, select the right technology pattern and evaluate prebuilt forecasting and recommendation services through explainability and scenario analysis.
Session | Learning Focus | Focused Theory Topics | Workshop / Lab Activity | Business Value & Measurable Outcomes | Architect Decision-Making & Outputs | Environment / Approved Tools
Session 1 | Business Value, Use-Case Triage and ADR | • Analytics vs ML vs GenAI vs Hybrid • Baseline, target, value hypothesis and KPI ownership • Architecture Decision Records and rejected options • Cost, latency, risk, explainability and operating-model considerations | Architecture workshop: • Classify selected retail use cases • Connect Analytics, demand forecasting, recommendations and next-best-action into one decision chain • Define baseline and success KPIs • Prepare and defend one priority ADR | Objective: Avoid overengineering and align investment to measurable retail outcomes. KPIs: expected value, feasibility, time-to-value, run cost and architecture risk. | Decide the correct technology pattern and document trade-offs. Live outputs: Triage Matrix, Business Value & KPI Canvas and one defended ADR. Take-away: complete a second ADR. | Facilitated workshop using supplied retail scenarios and templates.
Session 2 | Analytics Interpretation and ML Service Consumption | • Analytics as the trusted numerical layer • Training vs inference and ML model contracts • Demand-forecast and recommendation architectures • Metrics, confidence, latency, cost, drift and ownership | Guided integration: • Interpret a sales, inventory and promotion dashboard export • Invoke prebuilt forecast and recommendation endpoints • Inspect schemas, versions, metrics and operating limits • Compare Analytics, ML and LLM paths for one retail question | Objective: Improve replenishment and offer relevance through measurable predictive services. KPIs: numeric accuracy, forecast error, stockout exposure, Precision@K, latency and inference cost. | Determine whether each model is suitable for advisory, automated or human-reviewed use. Outputs: grounded briefing, ML Model Contract and Feasibility Scorecard. | VS Code, Python, Azure GPT and pre-deployed ML APIs. No participant model training.
Session 3 | Explainability and What-If Decision Analysis | • Global vs local explainability • Feature importance, confidence and reason codes • Explainability vs causal explanation • Sensitivity and predictive scenario analysis • Audit and human-oversight requirements | Guided hands-on: • Inspect supplied explanation outputs • Run baseline, promotion and inventory-allocation scenarios • Compare projected sales, margin and stockout exposure • Record assumptions, uncertainty and limitations | Objective: Make predictions understandable and support evidence-based business decisions. KPIs: explanation completeness, scenario variance, decision confidence and human-review requirement. | Assess whether explanations are actionable and audit-ready. Outputs: Explainability Review Sheet and one completed What-If Scenario. Take-away: run additional scenarios. | Prebuilt endpoints with confidence, feature contribution and reason codes; supplied scenario notebook.
DAY 2 ¦ LLM Foundations, Enterprise RAG, Model Right-Sizing and Grounded Decision Support
Day objective: Use GenAI as the interaction and knowledge layer, build a grounded retail decision flow and make evidence-based model-selection choices.
Session | Learning Focus | Focused Theory Topics | Workshop / Lab Activity | Business Value & Measurable Outcomes | Architect Decision-Making & Outputs | Environment / Approved Tools
Session 1 | Secure LLM Consumption and Structured Outputs | • Enterprise LLM application flow, tokens and context • Prompt structure, constraints and examples • Structured outputs and schema validation • Hallucination, latency and token-cost awareness • LLM as explanation layer - not predictive replacement | Hands-on build: • Modify a supplied Python client • Convert an unstructured planner request into validated JSON • Add forecast and recommendation outputs as context • Handle one invalid-output scenario | Objective: Convert unstructured requests into consistent decision inputs. KPIs: extraction accuracy, schema-validity rate, processing time and manual-correction effort. | Define the boundary between generated interpretation and authoritative business data. Outputs: validated structured JSON and quality measurement. | VS Code, Python, Azure GPT
Session 2 | Enterprise RAG and Grounded Policy Response | • RAG ingestion, chunking, embeddings and indexing • Keyword, vector and hybrid retrieval • Metadata and access-aware filtering • Groundedness, citations and escalation • RAG sizing and retrieval-quality trade-offs | Scaffolded hands-on: • Use the prepared Azure AI Search index • Modify query, retrieval mode and metadata filters • Generate a policy-grounded explanation for a proposed action • Run a small supplied evaluation set | Objective: Improve policy compliance and reduce time locating approved guidance. KPIs: citation accuracy, groundedness, policy coverage, response time and escalation rate. | Determine when evidence is sufficient and when the workflow must stop or escalate. Outputs: grounded response, RAG evaluation results and sizing decision. Take-away: compare additional retrieval configurations. | Azure GPT, embedding deployment, Azure AI Search and synthetic retail policy documents. Index is prepared before training.
Session 3 | SLM/LLM Right-Sizing and Fine-Tuning Decisions | • SLM vs frontier LLM trade-offs • Capability, latency, cost and privacy • Prompting, RAG, tools, SLM and fine-tuning decision ladder • Fine-tuning for behavior vs RAG for knowledge • Chinchilla scaling intuition at architect level | Guided comparison and decision workshop: • Compare supplied SLM and GPT outputs • Record quality, latency and cost • Complete one routing/sizing exercise • Score one fine-tuning proposal • Select the model-routing pattern for the capstone | Objective: Achieve acceptable quality at sustainable cost and latency. KPIs: quality score, cost per request, latency and escalation percentage. | Defend which tasks use SLM, GPT, classical ML or deterministic logic. Outputs: model-routing decision and Fine-Tuning | Azure GPT and pre-deployed SLM endpoint. Fine-tuning execution is trainer-demonstrated only.
DAY 3 ¦ Multi-Agent Orchestration, MCP and Governance
Day objective: Coordinate prebuilt specialist capabilities, apply MCP and human approval, evaluate security and traces, and defend the complete production architecture.
Session | Learning Focus | Focused Theory Topics | Workshop / Lab Activity | Business Value & Measurable Outcomes | Architect Decision-Making & Outputs | Environment / Approved Tools
Session 1 | Single Agent to Supervisor–Specialist Orchestration | • Agent with tools vs workflow vs multi-agent • Supervisor and specialist patterns • Agent contracts, shared state and hand-offs • Conflict resolution, timeout, fallback and stopping conditions • When multi-agent architecture is unnecessary | Architecture workshop and guided integration: • Inspect a working single-agent flow • Review prebuilt Forecast, Recommendation, What-If, Policy and Action agents • Configure supervisor routing • Test one conflict, timeout and fallback • Inspect the decision trace | Objective: Coordinate specialist services into one traceable retail decision workflow. KPIs: routing accuracy, hand-off success, latency, cost and decision completeness. | Decide which components deserve autonomy and which remain deterministic services. Outputs: Agent Contract & Orchestration Map and updated Autonomy Matrix. | Azure GPT, prebuilt specialist agents, ML endpoints and supplied state/trace assets.
Session 2 & 3 | 1. MCP, Governed Action, Security and Evaluation 2. ML/LLM Operations Discussion | • MCP host, client, server and capability discovery • MCP vs direct API vs agent-to-agent communication • Authentication, authorization and tool allow-lists • Prompt injection, excessive agency and sensitive-data risks • Foundry Tracing, Application Insights and Foundry Evaluation • End-to-end retail architecture and business-value realization • Analytics, ML, explainability, RAG, agents, MCP and human approval • MLOps/LLMOps alignment, versioning, monitoring and rollback • Prototype completeness vs production readiness | Guided integration and threat-modelling: • Inspect the prebuilt dummy MCP server • Invoke one read-only tool • Invoke one write tool only after human approval • Run supplied attack and unauthorized-tool scenarios • Review agent hand-offs, tools, tokens, latency and errors | Objective: Standardize enterprise capability access while preserving control and auditability. KPIs: approval compliance, unauthorized-action prevention, action success, blocked-attack rate and trace completeness. | Define MCP permission scope, approval boundaries and release-blocking controls. Outputs: MCP Trust Boundary, Risk Register, trace evidence and Evaluation Scorecard. | Dummy MCP server, Azure Function/REST API, Foundry Tracing, Application Insights and Foundry Evaluation.
DAY 4 ¦ Integrated Retail Capstone
Day objective: Coordinate prebuilt specialist capabilities, apply MCP and human approval, evaluate security and traces, and defend the complete production architecture.
Session | Learning Focus | Workshop / Lab Activity |  | Business Value & Measurable Outcomes | Architect Decision-Making & Outputs | Environment / Approved Tools
Session 1&2 | Integrated Capstone and Architecture Defence | Group capstone using the starter solution: • Identify a priority retail exception • Invoke forecast and recommendation services • Review explainability and one what-if scenario • Orchestrate specialists to select next best action • Ground the action through RAG • Invoke an MCP capability and approved write action • Review evaluation and traces • Present the final architecture Alternative track: defend a no-GenAI real-time fraud-scoring architecture. |  | Objective: Demonstrate how retail predictions become measurable, policy-compliant and governed actions. KPIs: model quality, scenario value, policy compliance, action acceptance, latency, cost and production readiness. | Present business value, architecture, KPIs, explainability, agent/MCP boundaries, risks and revised ADR. Outputs: integrated prototype or defended no-GenAI design, Evaluation Scorecard and Production Readiness Gate. | Starter application, prepared AI Search index, prebuilt endpoints and agents, MCP server, deployment template and evaluation dataset.
Post-Program Take-Away Reinforcement
Area | Assignment | Purpose | Expected Output | Estimated Effort | Review Mechanism | Introduced Live
Architecture | Complete the second ADR and refine the Business Value & KPI Canvas | Reinforce technology-selection judgment | Final ADR and measurable outcome map | 45–60 minutes | Reference answer and self-review checklist | Day 1
ML / RAG | Run additional what-if and retrieval configurations | Extend experimentation beyond classroom time | Scenario comparison and retrieval-quality observations | 60–75 minutes | Supplied evaluation workbook | Days 1–2
Governance | Complete the Production Readiness Gate and alternative no-GenAI design | Consolidate governance and right-sizing decisions | Readiness assessment and defended architecture | 60 minutes | Optional trainer/client review session | Day 3
Delivery note: The 3.5 Day Training format preserves all major architecture areas through preconfigured services, selective hands-on integration and take-away reinforcement. Where deeper participant-led orchestration, troubleshooting, deployment and capstone defence are expected, an additional applied day is recommended.